## User Stories
CheckUpp — User Story Backlog
Mobile app (iOS / Android) · User stories traced to the Original Wireframes deck
ID | Epic | User Story | Wireframe Reference | Priority | Status
US-01 | Local Document Storage | As a signed-in user, when I add a document I want to choose whether it is stored locally or in the cloud, so that I control where my files live. | Slide 1 – Choose where to save | Must | To Do
US-02 | Local Document Storage | As a signed-in user, I want confirmation that my document was saved to my device so that I know I can find it later. | Slide 1 – Saved to your device | Should | To Do
US-03 | Local Document Storage | As a signed-in user, I want to save my documents to my device's local storage so that I can access them later outside the app. | Slide 2 – Document Wallet | Must | To Do
US-04 | e-Script Sharing | As a signed-in user, I want to save my e-Script as a link and view it as a QR code so that I can quickly share my prescription with a pharmacy or caregiver. | Slide 3 – Save as link / Show QR | Must | To Do
US-05 | e-Script Sharing | As a signed-in user, I want to display my e-Script as a QR code and share its link so that a pharmacist can scan or receive it directly. | Slide 3 – QR code & share link | Must | To Do
US-06 | e-Script Sharing | As a signed-in user, when I tap Save as link or Share, I want my phone's native share sheet to open so that I can send my e-Script through any app or contact I already use. | Slide 4 – Native share sheet | Should | To Do
US-07 | Cancer Screening | As a signed-in user, I want to take a live photo of my screening report with the camera or upload an existing photo or file from my device, so that my results are recorded accurately without manual entry. | Slide 5 – Capture & convert | Must | To Do
US-08 | Cancer Screening | As a signed-in user, I want to mark my screening result as normal or abnormal and add extra photos or files for more detail, so that my health record reflects the full outcome of the screening. | Slide 5 – Record screening result | Should | To Do
Priority uses MoSCoW (Must / Should / Could). Status and priority are starting values — adjust as the backlog is groomed. Wireframe references map to Slides 1–5 of the CheckUpp deck.